## Artifacts-Attributes-Risks
Rizikų naujas NR
Rizikų senas NR
[6 empty] | RC1 Requirements | RC1 Requirements | RC1 Requirements | RC1 Requirements | RC1 Requirements | RC1 Requirements |  | RC2 Project Management | RC2 Project Management |  | RC3 Communication | RC3 Communication | RC3 Communication | RC3 Communication | RC3 Communication | RC3 Communication | RC3 Communication | RC3 Communication |  | RC4 Technology | RC4 Technology | RC4 Technology |  | RC5 Design | RC5 Design | RC5 Design | RC5 Design | RC5 Design |  | RC6 Coding | RC6 Coding | RC6 Coding | RC6 Coding | RC6 Coding | RC6 Coding | RC6 Coding | RC6 Coding |  | RC7 Testing | RC7 Testing | RC7 Testing | RC7 Testing | RC7 Testing | RC7 Testing | RC7 Testing | RC7 Testing | RC7 Testing | RC7 Testing |  | RC8 Human | RC8 Human |  | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies | RC9 Agile Ceremonies
Sena numeracija | [5 empty] | R001 | R002 | R003 | R004 | R005 | R006 |  | R007 | R008 |  | R009 | R010 | R011 | R012 | R013 | R014 | R015 | R016 |  | R017 | R018 | R019 |  | R020 | R021 | R022 | R023 | R024 |  | R025 | R026 | R027 | R028 | R029 | R030 | R031 | R032 |  | R033 | R034 | R035 | R036 | R037 | R038 | R039 | R040 | R041 | R042 |  | R043 | R044 |  | R045 | R046 | R047 | R048 | R049 | R050 | R051 | R052 | R053 | R054 | R055 | R056 | R057 | R058
[6 empty] | Undefined requirements | Unclear requirements | Incorrectly defined requirements | Unmet requirements and scope creep | Resource misallocation due to many competing priorities | Poor prioritization and unclear vision |  | Lack of sufficient tasks for the team that match their competences | Lack of accountability in addressing missed deadlines and delayed sprints |  | Lack of communication among team members | Low client engagement and misalignment of requirements | Delays due to slow client responses | Unclear project vision and progress | Rework of completed tasks | Rework due to lack of communication | Poor communication | Lack of structured information |  | Excessive time on training | Inadequate understanding of Scrum processes | Inefficient onboarding process |  | Delays due to task interdependencies | Scope increase due to tasks dependencies | System-wide impact overlooked during task execution | Use of outdated software versions | Untraceable tasks |  | Difficult to maintain the code without code standards | Difficult to understand and support code | Reduced performance | Increasing technical debt | Poor code quality | Lack of code improvement support | Lack of code review feedback | Redundant development of existing functionality |  | Lack of attention to detail by testers | Testing lagging behind development in the sprint | Poor QA-developer collaboration leading to uncommunicated changes across the system | Insufficient unit testing by developers | Challenges in unit testing legacy code | Lack of test scenarios for QA specialists | Unassessed impact of changes on other system areas | Overwriting documentation among team members | Outdated documentation | Dependency on key team members due to poor documentation |  | Overlooking team expertise due to inadequate task allocation | Shortage of necessary specialists in team |  | Inefficient Scrum integration | Overestimated tasks | Underestimated tasks | Inaccurate task evaluation without full requirement insight | Tasks evaluated without technical constraints in mind | Ineffective retrospective meetings | Decreasing scope completion in sprint | Increased sprint output with decreased quality | Mismatch in planned and actual sprint task completion | Inefficient task splitting | Excessive number of small tasks | Insufficient sprint backlog | Overloaded sprint backlog | Inaccurate sprint velocity forecasting
[5 empty] | 2296 | 41 | 60 | 38 | 88 | 25 | 79 |  | 51 | 92 | 0 | 50 | 73 | 45 | 72 | 32 | 26 | 59 | 49 | 0 | 3 | 65 | 4 | 0 | 66 | 58 | 51 | 6 | 10 | 0 | 49 | 33 | 46 | 34 | 49 | 10 | 13 | 5 | 0 | 19 | 22 | 41 | 32 | 32 | 44 | 43 | 7 | 26 | 16 | 0 | 46 | 75 | 0 | 75 | 28 | 32 | 81 | 79 | 7 | 52 | 16 | 22 | 18 | 24 | 30 | 12 | 35 | 0
|  |  | AR01 | Product | 597 | 23 | 20 | 11 | 21 | 13 | 27 |  | 19 | 22 | 0 | 9 | 26 | 13 | 27 | 7 | 6 | 15 | 17 | 0 | 1 | 16 | 1 | 0 | 14 | 11 | 20 | 2 | 5 | 0 | 8 | 3 | 3 | 10 | 6 | 2 | 3 | 1 | 0 | 1 | 2 | 6 | 1 | 1 | 12 | 16 | 2 | 9 | 6 | 0 | 11 | 15 | 0 | 24 | 5 | 5 | 14 | 12 | 2 | 16 | 1 | 4 | 8 | 13 | 18 | 4 | 7 | 0
| AR01.1 | Product Backlog | AR01.1 | Product Backlog | 138 | 6 | 5 | 3 | 4 | 4 | 8 |  | 6 | 7 |  | 0 | 8 | 3 | 7 | 3 | 2 | 4 | 5 |  | 0 | 4 | 0 |  | 6 | 3 | 4 | 0 | 2 |  | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 1 | 1 |  | 3 | 4 |  | 7 | 1 | 0 | 1 | 1 | 0 | 2 | 0 | 0 | 2 | 4 | 5 | 1 | 0
| AR01.1 | Product Backlog | AT001 | Number of errors | 15 |  | x | x | x |  |  | 3 |  | x | 1 |  | x |  |  | x |  |  |  | 2 |  |  |  | 0 | x | x |  |  |  | 2 |  |  | x |  | x |  |  |  | 2 | x |  |  |  |  | x | x |  |  | x | 4 |  |  | 0 | [14 empty] | 1 | bar: R045
| AR01.1 | Product Backlog | AT005 | Number of ready tasks | 18 | x | x |  | x |  | x | 4 | x | x | 2 |  | x | x | x |  |  | x | x | 5 |  | x |  | 1 | x |  |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 | x |  | 1 | [14 empty] | 4 | bar: R045; R051; R055 to R056
| AR01.1 | Product Backlog | AT033 | Average of tasks in epic | 12 | x |  |  |  |  | x | 2 | x |  | 1 |  | x |  | x |  | x |  | x | 4 |  |  |  | 0 | x |  |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 4 | bar: R054 to R057
| AR01.1 | Product Backlog | AT035 | Number of prepared sprints | 16 | x | x |  |  |  | x | 3 |  | x | 1 |  | x | x | x |  |  | x | x | 5 |  | x |  | 1 | x |  |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 |  | x | 1 | [14 empty] | 4 | bar: R045; R051; R055 to R056
| AR01.1 | Product Backlog | AT036 | Percentage of high-priority tasks | 19 |  |  | x | x | x | x | 4 | x | x | 2 |  |  |  | x |  |  | x |  | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 | [6 empty] | x |  |  |  | 1 | x | x | 2 | [14 empty] | 4 | bar: R045 to R046; R048 to R049
| AR01.1 | Product Backlog | AT037 | Percentage of low-priority tasks | 11 |  |  |  |  | x | x | 2 | x |  | 1 |  | x | x | x |  |  |  |  | 3 |  | x |  | 1 | [5 empty] | 0 | [8 empty] | 0 | [10 empty] | 0 | x | x | 2 | [14 empty] | 2 | bar: R045; R056
| AR01.1 | Product Backlog | AT041 | Number of tasks without epic | 12 |  | x | x |  |  | x | 3 |  |  | 0 |  | x |  | x | x |  |  | x | 4 |  |  |  | 0 |  |  | x |  | x | 2 | [8 empty] | 0 | [5 empty] | x |  |  | x |  | 2 |  |  | 0 | [14 empty] | 1 | bar: R045
| AR01.1 | Product Backlog | AT042 | Number of epics | 14 | x |  |  |  | x | x | 3 | x | x | 2 |  | x |  | x |  |  |  |  | 2 |  |  |  | 0 |  |  | x |  |  | 1 | x | [7 empty] | 1 | [6 empty] | x |  |  |  | 1 |  |  | 0 | [14 empty] | 4 | bar: R045; R054 to R056
| AR01.1 | Product Backlog | AT046 | Number of initial tasks | 9 | x | x |  |  | x | x | 4 |  | x | 1 |  | x |  |  |  |  | x | x | 3 |  |  |  | 0 |  |  |  |  | x | 1 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 0
| AR01.1 | Product Backlog | AT047 | Number of technical tasks | 12 | x |  |  | x |  |  | 2 | x | x | 2 |  |  |  |  | x | x |  |  | 2 |  |  |  | 0 | x | x | x |  |  | 3 |  |  |  | x |  |  |  |  | 1 | [6 empty] | x |  |  |  | 1 |  | x | 1 | [14 empty] | 0
| AR01.2 | Product Goal | AR01.2 | Product Goal | 67 | 3 | 2 | 1 | 1 | 1 | 3 |  | 2 | 2 |  | 2 | 3 | 1 | 3 | 1 | 0 | 2 | 3 |  | 1 | 2 | 1 |  | 1 | 0 | 3 | 1 | 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 2 | 1 |  | 0 | 3 |  | 4 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 2 | 2 | 0 | 1
| AR01.2 | Product Goal | AT013 | Average training time per person | 10 | [6 empty] | 0 | x |  | 1 | x | [5 empty] | x |  | 2 | x | x | x | 3 | [5 empty] | 0 | [8 empty] | 0 |  |  | x | [7 empty] | 1 |  | x | 1 | [14 empty] | 2 | bar: R045; R058
| AR01.2 | Product Goal | AT029 | Periodicity of documentation review | 14 |  |  |  | x |  |  | 1 |  |  | 0 | x | [6 empty] | x | 2 |  |  |  | 0 |  |  | x | x | x | 3 | [8 empty] | 0 | [5 empty] | x | x | x | x | x | 5 |  | x | 1 | [14 empty] | 2 | bar: R048 to R049
| AR01.2 | Product Goal | AT035 | Number of prepared sprints | 16 | x | x |  |  |  | x | 3 |  | x | 1 |  | x | x | x |  |  | x | x | 5 |  | x |  | 1 | x |  |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 |  | x | 1 | [14 empty] | 4 | bar: R045; R051; R055 to R056
| AR01.2 | Product Goal | AT041 | Number of tasks without epic | 13 | x | x | x |  |  | x | 4 |  |  | 0 |  | x |  | x | x |  |  | x | 4 |  |  |  | 0 |  |  | x |  | x | 2 | [8 empty] | 0 | [5 empty] | x |  |  | x |  | 2 |  |  | 0 | [14 empty] | 1 | bar: R045
| AR01.2 | Product Goal | AT042 | Number of epics | 14 | x |  |  |  | x | x | 3 | x | x | 2 |  | x |  | x |  |  |  |  | 2 |  |  |  | 0 |  |  | x |  |  | 1 | x | [7 empty] | 1 | [6 empty] | x |  |  |  | 1 |  |  | 0 | [14 empty] | 4 | bar: R045; R054 to R056
| AR01.3 | Epic Discovery | AR01.3 | Epic Discovery | 106 | 5 | 5 | 3 | 5 | 1 | 3 |  | 0 | 3 |  | 4 | 3 | 2 | 4 | 1 | 2 | 3 | 3 |  | 0 | 2 | 0 |  | 0 | 1 | 4 | 0 | 0 |  | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 |  | 0 | 0 | 1 | 0 | 0 | 4 | 3 | 0 | 4 | 2 |  | 2 | 2 |  | 3 | 1 | 1 | 4 | 3 | 1 | 4 | 0 | 2 | 0 | 0 | 2 | 0 | 3
| AR01.3 | Epic Discovery | AT010 | Design file | 14 | x | x | x | x |  |  | 4 |  |  | 0 |  |  |  | x |  |  |  |  | 1 |  |  |  | 0 |  |  | x |  |  | 1 | [8 empty] | 0 | [5 empty] | x | x |  | x | x | 4 |  |  | 0 | [14 empty] | 4 | bar: R045 to R048
| AR01.3 | Epic Discovery | AT011 | Customer response time | 25 | x | x | x | x | x | x | 6 |  |  | 0 | x | x | x | x | x |  | x | x | 7 |  | x |  | 1 |  |  | x |  |  | 1 | [8 empty] | 0 | [5 empty] | x | x |  | x |  | 3 |  |  | 0 | [14 empty] | 7 | bar: R045; R048 to R049; R051; R053; R056; R058
| AR01.3 | Epic Discovery | AT012 | Team response time | 17 | x | x |  | x |  |  | 3 |  | x | 1 | x |  |  |  |  | x | x | x | 4 |  | x |  | 1 |  |  | x |  |  | 1 |  |  |  | x |  | x | x |  | 3 | [10 empty] | 0 |  | x | 1 | [14 empty] | 3 | bar: R045; R050 to R051
| AR01.3 | Epic Discovery | AT027 | Number of reopened tasks | 33 | x | x | x | x |  | x | 5 |  | x | 1 | x | x |  | x |  | x | x | x | 6 |  |  |  | 0 |  | x | x |  |  | 2 | x | x | x | x | x |  | x | x | 7 |  |  | x |  |  | x | x |  | x | x | 5 | x | x | 2 | [14 empty] | 5 | bar: R048 to R049; R051; R053; R058
| AR01.3 | Epic Discovery | AT048 | Number of in-preparation tasks | 17 | x | x |  | x |  | x | 4 |  | x | 1 | x | x | x | x |  |  |  |  | 4 |  |  |  | 0 | [5 empty] | 0 | [8 empty] | 0 | [5 empty] | x |  |  | x |  | 2 | x |  | 1 | [14 empty] | 5 | bar: R048 to R049; R051; R056; R058
| AR01.4 | Design discovery | AR01.4 | Design discovery | 55 | 3 | 3 | 2 | 3 | 1 | 1 |  | 0 | 1 | 0 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0
| AR01.4 | Design discovery | AT010 | Design file | 14 | x | x | x | x |  |  | 4 |  |  | 0 |  |  |  | x |  |  |  |  | 1 |  |  |  | 0 |  |  | x |  |  | 1 | [8 empty] | 0 | [5 empty] | x | x |  | x | x | 4 |  |  | 0 | [14 empty] | 4 | bar: R045 to R048
| AR01.4 | Design discovery | AT011 | Customer response time | 24 | x | x | x | x | x | x | 6 |  |  | 0 | x | x | x | x | x |  | x | x | 7 |  | x |  | 1 |  |  | x |  |  | 1 | [8 empty] | 0 | [5 empty] | x | x |  |  |  | 2 |  |  | 0 | [14 empty] | 7 | bar: R045; R048 to R049; R051; R053; R056; R058
| AR01.4 | Design discovery | AT012 | Team response time | 17 | x | x |  | x |  |  | 3 |  | x | 1 | x |  |  |  |  | x | x | x | 4 |  | x |  | 1 |  |  | x |  |  | 1 |  |  |  | x |  | x | x |  | 3 | [10 empty] | 0 |  | x | 1 | [14 empty] | 3 | bar: R045; R050 to R051
| AR01.5 | Technical debt backlog | AR01.5 | Technical debt backlog | 145 | 3 | 4 | 2 | 5 | 4 | 7 |  | 6 | 6 | 0 | 1 | 6 | 5 | 6 | 1 | 0 | 3 | 1 | 0 | 0 | 4 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 2 | 1 | 1 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 4 | 2 | 2 | 5 | 5 | 0 | 5 | 1 | 1 | 2 | 3 | 4 | 1 | 2 | 0
| AR01.5 | Technical debt backlog | AT005 | Number of ready tasks | 20 | x | x |  | x |  | x | 4 | x | x | 2 |  | x | x | x |  |  | x | x | 5 |  | x |  | 1 | x |  |  |  |  | 1 |  |  |  | x | x |  |  |  | 2 | [10 empty] | 0 | x |  | 1 | [14 empty] | 4 | bar: R045; R051; R055 to R056
| AR01.5 | Technical debt backlog | AT008 | Estimate | 22 |  | x |  | x |  | x | 3 |  | x | 1 |  | x | x | [5 empty] | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 |  |  | x | x | x | x | x |  |  |  | 5 | x |  | 1 | [14 empty] | 6 | bar: R046 to R049; R054 to R055
| AR01.5 | Technical debt backlog | AT022 | Number of blocked tasks | 22 |  | x | x | x |  | x | 4 |  | x | 1 | x | x | x | x |  |  | x |  | 5 |  |  |  | 0 | x | x | x |  |  | 3 |  |  |  | x | x |  |  |  | 2 |  |  | x |  |  | x |  |  |  |  | 2 |  | x | 1 | [14 empty] | 4 | bar: R048 to R049; R051; R058
| AR01.5 | Technical debt backlog | AT030 | Percentage of dependent tasks | 23 |  |  |  | x | x | x | 3 | x |  | 1 |  | x |  | x |  |  |  |  | 2 |  |  |  | 0 |  | x | x |  |  | 2 | x | x |  | x | x |  |  |  | 4 |  | x | x |  |  |  | x |  |  |  | 3 |  |  | 0 | [14 empty] | 8 | bar: R047 to R049; R051; R054 to R057
| AR01.5 | Technical debt backlog | AT036 | Percentage of high-priority tasks | 19 |  |  | x | x | x | x | 4 | x | x | 2 |  |  |  | x |  |  | x |  | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 | [6 empty] | x |  |  |  | 1 | x | x | 2 | [14 empty] | 4 | bar: R045 to R046; R048 to R049
| AR01.5 | Technical debt backlog | AT037 | Percentage of low-priority tasks | 11 |  |  |  |  | x | x | 2 | x |  | 1 |  | x | x | x |  |  |  |  | 3 |  | x |  | 1 | [5 empty] | 0 | [8 empty] | 0 | [10 empty] | 0 | x | x | 2 | [14 empty] | 2 | bar: R045; R056
| AR01.5 | Technical debt backlog | AT039 | Standard deviation of number of tasks | 19 | x | x |  |  | x | x | 4 | x | x | 2 |  | x | x | x |  |  |  |  | 3 |  |  |  | 0 | [5 empty] | 0 | [8 empty] | 0 | [10 empty] | 0 | x | x | 2 | [14 empty] | 8 | bar: R045; R048 to R049; R051 to R053; R056; R058
| AR01.5 | Technical debt backlog | AT046 | Number of initial tasks | 9 | x | [5 empty] | 1 | x | x | 2 |  |  |  |  | x |  |  |  | 1 |  |  |  | 0 | [5 empty] | 0 | x |  | x | x |  |  |  |  | 3 | [10 empty] | 0 |  | x | 1 | [14 empty] | 1 | bar: R051
| AR01.6 | Product roadmap | AR01.6 | Product roadmap | 86 | 3 | 1 | 0 | 3 | 2 | 5 |  | 5 | 3 | 0 | 0 | 5 | 1 | 5 | 0 | 1 | 1 | 3 | 0 | 0 | 2 | 0 | 0 | 3 | 3 | 2 | 1 | 1 | 0 | 3 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 3 | 4 | 4 | 2 | 0 | 0
| AR01.6 | Product roadmap | AT005 | Number of ready tasks | 18 | x | x |  | x |  | x | 4 | x | x | 2 |  | x | x | x |  |  | x | x | 5 |  | x |  | 1 | x |  |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 | x |  | 1 | [14 empty] | 4 | bar: R045; R051; R055 to R056
| AR01.6 | Product roadmap | AT030 | Percentage of dependent tasks | 23 |  |  |  | x | x | x | 3 | x |  | 1 |  | x |  | x |  |  |  |  | 2 |  |  |  | 0 |  | x | x |  |  | 2 | x | x |  | x | x |  |  |  | 4 |  | x | x |  |  |  | x |  |  |  | 3 |  |  | 0 | [14 empty] | 8 | bar: R047 to R049; R051; R054 to R057
| AR01.6 | Product roadmap | AT031 | Number of open versions | 18 |  |  |  | x |  | x | 2 | x | x | 2 |  | x |  | x |  |  |  | x | 3 |  | x |  | 1 | x | x |  | x | x | 4 | x |  |  | x |  |  |  |  | 2 | [7 empty] | x | x | x | 3 |  |  | 0 | [14 empty] | 1 | bar: R045
| AR01.6 | Product roadmap | AT033 | Average of tasks in epic | 13 | x |  |  |  |  | x | 2 | x |  | 1 |  | x |  | x |  | x |  | x | 4 |  |  |  | 0 | x | x |  |  |  | 2 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 4 | bar: R054 to R057
| AR01.6 | Product roadmap | AT042 | Number of epics | 14 | x |  |  |  | x | x | 3 | x | x | 2 |  | x |  | x |  |  |  |  | 2 |  |  |  | 0 |  |  | x |  |  | 1 | x | [7 empty] | 1 | [6 empty] | x |  |  |  | 1 |  |  | 0 | [14 empty] | 4 | bar: R045; R054 to R056
|  |  | AR02 | Sprint | 1053 | 10 | 28 | 13 | 38 | 11 | 28 |  | 21 | 41 | 0 | 21 | 28 | 19 | 27 | 17 | 15 | 26 | 23 | 0 | 2 | 27 | 3 | 0 | 29 | 31 | 23 | 1 | 2 | 0 | 22 | 18 | 29 | 17 | 29 | 6 | 8 | 3 | 0 | 10 | 10 | 21 | 18 | 18 | 16 | 18 | 2 | 11 | 7 | 0 | 24 | 36 | 0 | 32 | 14 | 14 | 42 | 42 | 4 | 25 | 7 | 15 | 8 | 9 | 10 | 6 | 18 | 0
| AR02.1 | Sprint backlog | AR02.1 | Sprint backlog | 614 | 5 | 15 | 8 | 20 | 7 | 18 |  | 13 | 22 | 0 | 10 | 16 | 10 | 18 | 10 | 7 | 12 | 12 | 0 | 0 | 16 | 0 | 0 | 18 | 20 | 12 | 0 | 1 | 0 | 13 | 12 | 16 | 10 | 19 | 3 | 4 | 2 | 0 | 8 | 9 | 14 | 12 | 12 | 10 | 10 | 0 | 6 | 1 | 0 | 14 | 19 | 0 | 17 | 8 | 8 | 25 | 25 | 1 | 15 | 6 | 12 | 4 | 5 | 7 | 6 | 11 | 0
| AR02.1 | Sprint backlog | AT001 | Number of errors | 22 |  | x | x | x |  |  | 3 |  | x | 1 |  | x |  |  | x |  |  |  | 2 |  |  |  | 0 | x | x |  |  |  | 2 |  |  | x |  | x |  |  |  | 2 | x | x | x | x | x | x |  |  |  |  | 6 |  |  | 0 | [14 empty] | 6 | bar: R045; R048 to R049; R051 to R053
| AR02.1 | Sprint backlog | AT002 | Standard deviation of errors | 22 |  | x | x | x |  |  | 3 |  | x | 1 |  | x |  |  | x |  |  |  | 2 |  |  |  | 0 | x | x |  |  |  | 2 |  |  | x |  | x |  |  |  | 2 | x | x | x | x | x | x |  |  |  |  | 6 |  |  | 0 | [14 empty] | 6 | bar: R045; R048 to R049; R051 to R053
| AR02.1 | Sprint backlog | AT003 | Velocity | 24 |  |  |  | x |  |  | 1 | x |  | 1 |  |  |  | x |  |  |  |  | 1 |  | x |  | 1 | x | x |  |  |  | 2 |  |  |  | x | x |  |  |  | 2 | x | x | x | [7 empty] | 3 | x | x | 2 | [14 empty] | 11 | bar: R045 to R049; R051 to R053; R056 to R058
| AR02.1 | Sprint backlog | AT004 | Standard deviation of velocity | 24 |  |  |  | x |  |  | 1 | x |  | 1 |  |  |  | x |  |  |  |  | 1 |  | x |  | 1 | x | x |  |  |  | 2 |  |  |  | x | x |  |  |  | 2 | x | x | x | [7 empty] | 3 | x | x | 2 | [14 empty] | 11 | bar: R045 to R049; R051 to R053; R056 to R058
| AR02.1 | Sprint backlog | AT005 | Number of ready tasks | 19 | x | x |  | x |  | x | 4 | x | x | 2 |  | x | x | x |  |  | x | x | 5 |  | x |  | 1 | x |  |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 | x |  | 1 | [14 empty] | 5 | bar: R045; R051; R055 to R057
| AR02.1 | Sprint backlog | AT007 | Number of subtasks of task | 7 |  |  | x |  |  |  | 1 |  |  | 0 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | [5 empty] | x | x |  | 2 | [10 empty] | 0 |  |  | 0 | [14 empty] | 4 | bar: R048 to R049; R054 to R055
| AR02.1 | Sprint backlog | AT008 | Estimate | 23 |  | x |  | x |  | x | 3 |  | x | 1 |  | x | x | [5 empty] | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 |  |  | x | x | x | x | x |  |  |  | 5 | x |  | 1 | [14 empty] | 7 | bar: R046 to R049; R054 to R055; R058
| AR02.1 | Sprint backlog | AT009 | Percentage difference between velocity and implemented scope | 33 |  | x |  | x |  | x | 3 | x | x | 2 | x |  |  | x |  |  |  | x | 3 |  | x |  | 1 | x | x | x |  |  | 3 |  | x | x | x | x |  |  |  | 4 | x | x | x | x | x | x | x |  |  |  | 7 | x | x | 2 | [14 empty] | 8 | bar: R045 to R049; R051; R053; R058
| AR02.1 | Sprint backlog | AT014 | Average of sub-tasks of task | 9 |  |  |  |  | x |  | 1 |  |  | 0 |  | x |  |  | x | x | x | x | 5 |  |  |  | 0 |  | x |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 2 | bar: R048 to R049
| AR02.1 | Sprint backlog | AT015 | Standard deviation of sub-tasks | 9 |  |  |  |  | x |  | 1 |  |  | 0 |  | x |  |  | x | x | x | x | 5 |  |  |  | 0 |  | x |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 2 | bar: R048 to R049
| AR02.1 | Sprint backlog | AT016 | Average time spent on code review | 19 |  |  |  | x |  |  | 1 | x | x | 2 |  |  |  |  | x | x |  |  | 2 |  | x |  | 1 | [5 empty] | 0 | x | x | x |  | x | x | x |  | 6 |  |  |  | x | x |  |  |  | x |  | 3 | x | x | 2 | [14 empty] | 2 | bar: R048 to R049
| AR02.1 | Sprint backlog | AT017 | Number of people doing code review | 12 | [6 empty] | 0 |  |  | 0 | x | [5 empty] | x |  | 2 |  |  |  | 0 | [5 empty] | 0 | x | x | x |  |  | x |  |  | 4 |  |  |  |  | x | [5 empty] | 1 | x | x | 2 | [14 empty] | 3 | bar: R045; R048 to R049
| AR02.1 | Sprint backlog | AT018 | Number of comments after code review | 16 |  | x |  |  |  |  | 1 |  | x | 1 | x |  |  |  |  | x | x | x | 4 |  |  |  | 0 | [5 empty] | 0 | x | x | x | x | x |  | x |  | 6 | [10 empty] | 0 |  | x | 1 | [14 empty] | 3 | bar: R047 to R049
| AR02.1 | Sprint backlog | AT019 | Average of unit tests for task | 8 | [6 empty] | 0 |  | x | 1 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | x | x | x |  | x |  |  |  | 4 |  |  |  | x | x | [5 empty] | 2 |  | x | 1 | [14 empty] | 0
| AR02.1 | Sprint backlog | AT020 | Average of automated tests per task | 7 | [6 empty] | 0 |  | x | 1 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | x | x | x |  | x |  |  |  | 4 |  |  |  | x | [6 empty] | 1 |  | x | 1 | [14 empty] | 0
| AR02.1 | Sprint backlog | AT021 | Average number of code returns to execution stage after review | 17 |  | x |  |  |  |  | 1 |  | x | 1 | x |  |  |  |  | x |  |  | 2 |  |  |  | 0 | x | x |  |  |  | 2 | x | x | x | x | x |  |  | x | 6 | [8 empty] | x |  | 1 | x | x | 2 | [14 empty] | 2 | bar: R048 to R049
| AR02.1 | Sprint backlog | AT022 | Number of blocked tasks | 22 |  | x | x | x |  | x | 4 |  | x | 1 | x | x | x | x |  |  | x |  | 5 |  |  |  | 0 | x | x | x |  |  | 3 |  |  |  | x | x |  |  |  | 2 |  |  | x |  |  | x |  |  |  |  | 2 |  | x | 1 | [14 empty] | 4 | bar: R048 to R049; R051; R058
| AR02.1 | Sprint backlog | AT023 | Sprint delay in days | 23 |  |  |  | x |  | x | 2 |  | x | 1 |  | x | x |  | x |  |  |  | 3 |  | x |  | 1 | x | x |  |  |  | 2 |  |  |  |  | x |  |  |  | 1 | x | x |  | x | x |  | x |  |  |  | 5 |  |  | 0 | [14 empty] | 8 | bar: R045 to R046; R048 to R049; R051; R053; R057 to R058
| AR02.1 | Sprint backlog | AT024 | Time is allocated for demonstration meetings | 9 |  |  |  | x |  | x | 2 |  |  | 0 |  |  |  | x |  |  | x | x | 3 |  | x |  | 1 | [5 empty] | 0 | [8 empty] | 0 |  |  | x | [7 empty] | 1 |  | x | 1 | [14 empty] | 1 | bar: R045
| AR02.1 | Sprint backlog | AT025 | Time is reserved for retrospective meetings | 7 |  |  |  | x |  |  | 1 |  |  | 0 |  |  |  | x |  |  | x | x | 3 |  | x |  | 1 | [5 empty] | 0 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 2 | bar: R045; R050
| AR02.1 | Sprint backlog | AT026 | Percentage of time in meetings out of total team work time | 14 |  |  |  | x |  | x | 2 |  | x | 1 | x |  | x | x |  |  | x | x | 5 |  | x |  | 1 | [5 empty] | 0 |  |  | x |  | x |  |  |  | 2 | [10 empty] | 0 | x | x | 2 | [14 empty] | 1 | bar: R045
| AR02.1 | Sprint backlog | AT027 | Number of reopened tasks | 33 | x | x | x | x |  | x | 5 |  | x | 1 | x | x |  | x |  | x | x | x | 6 |  |  |  | 0 |  | x | x |  |  | 2 | x | x | x | x | x |  | x | x | 7 |  |  | x |  |  | x | x |  | x | x | 5 | x | x | 2 | [14 empty] | 5 | bar: R048 to R049; R051; R053; R058
| AR02.1 | Sprint backlog | AT028 | Number of hotfix | 29 | x | x | x | x | x | x | 6 |  | x | 1 | x |  |  | x | x |  |  |  | 3 |  | x |  | 1 | x | x | x |  |  | 3 | x |  | x |  | x |  |  |  | 3 | x |  | x |  |  | x | x |  | x |  | 5 | x | x | 2 | [14 empty] | 5 | bar: R048 to R049; R051; R053; R058
| AR02.1 | Sprint backlog | AT030 | Percentage of dependent tasks | 23 |  |  |  | x | x | x | 3 | x |  | 1 |  | x |  | x |  |  |  |  | 2 |  |  |  | 0 |  | x | x |  |  | 2 | x | x |  | x | x |  |  |  | 4 |  | x | x |  |  |  | x |  |  |  | 3 |  |  | 0 | [14 empty] | 8 | bar: R047 to R049; R051; R054 to R057
| AR02.1 | Sprint backlog | AT032 | Standard deviation of scope | 34 |  |  |  | x |  | x | 2 | x | x | 2 | x | x | x | x | x | x | x | x | 8 |  | x |  | 1 | x | x |  |  |  | 2 | x | x | x | x | x |  |  |  | 5 | x | x | x | x | x | [5 empty] | 5 |  | x | 1 | [14 empty] | 8 | bar: R045 to R049; R052 to R053; R058
| AR02.1 | Sprint backlog | AT036 | Percentage of high-priority tasks | 19 |  |  | x | x | x | x | 4 | x | x | 2 |  |  |  | x |  |  | x |  | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 | [6 empty] | x |  |  |  | 1 | x | x | 2 | [14 empty] | 4 | bar: R045 to R046; R048 to R049
| AR02.1 | Sprint backlog | AT037 | Percentage of low-priority tasks | 12 |  |  |  |  | x | x | 2 | x |  | 1 |  | x | x | x |  |  |  |  | 3 |  | x |  | 1 | [5 empty] | 0 | [8 empty] | 0 | [10 empty] | 0 | x | x | 2 | [14 empty] | 3 | bar: R045; R053; R056
| AR02.1 | Sprint backlog | AT039 | Standard deviation of number of tasks | 29 | x | x |  |  | x | x | 4 | x | x | 2 |  | x | x | x |  |  |  |  | 3 |  |  |  | 0 | x | x |  |  |  | 2 | x | x | x | x | x |  |  |  | 5 |  |  |  | x | x |  |  |  | x |  | 3 |  | x | 1 | [14 empty] | 9 | bar: R045; R048 to R049; R051 to R053; R056 to R058
| AR02.1 | Sprint backlog | AT040 | Percentage of tech tasks | 17 |  |  |  | x |  | x | 2 | x | x | 2 |  |  |  |  | x |  |  | x | 2 |  |  |  | 0 | x | x | x |  |  | 3 | x | x | [6 empty] | 2 | [5 empty] | x | x |  |  |  | 2 |  | x | 1 | [14 empty] | 3 | bar: R048 to R049; R051
| AR02.1 | Sprint backlog | AT041 | Number of tasks without epic | 12 |  | x | x |  |  | x | 3 |  |  | 0 |  | x |  | x | x |  |  | x | 4 |  |  |  | 0 |  |  | x |  | x | 2 | [8 empty] | 0 | [5 empty] | x |  |  | x |  | 2 |  |  | 0 | [14 empty] | 1 | bar: R045
| AR02.1 | Sprint backlog | AT050 | Number of in-development tasks | 24 | x | x |  |  |  | x | 3 | x | x | 2 |  | x | x | x |  |  |  |  | 3 |  | x |  | 1 | x | x | x |  |  | 3 | x |  | x |  | x |  |  |  | 3 |  | x | x | x | x |  | x |  |  |  | 5 |  |  | 0 | [14 empty] | 4 | bar: R048 to R049; R051; R056
| AR02.1 | Sprint backlog | AT051 | Average of Estimate of Task | 22 |  | x |  | x |  | x | 3 |  | x | 1 |  | x | x | [5 empty] | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 |  |  | x | x | x | x | x |  |  |  | 5 | x |  | 1 | [14 empty] | 6 | bar: R046 to R049; R054 to R055
| AR02.1 | Sprint backlog | AT052 | Number of Estimated Tasks | 14 |  | x |  |  |  |  | 1 | x | x | 2 | x |  |  | x |  |  |  |  | 2 |  |  |  | 0 | x |  | x | [5 empty] | x | [5 empty] | 1 | [10 empty] | 0 |  |  | 0 | [14 empty] | 6 | bar: R045; R048 to R049; R051; R053; R058
| AR02.2 | Epic implementation | AR02.2 | Epic implementation | 350 | 5 | 13 | 5 | 12 | 4 | 9 |  | 5 | 17 |  | 8 | 11 | 8 | 8 | 7 | 7 | 11 | 9 |  | 0 | 9 | 0 |  | 10 | 10 | 9 | 0 | 1 |  | 8 | 6 | 10 | 6 | 9 | 3 | 3 | 1 |  | 1 | 1 | 5 | 6 | 6 | 6 | 7 | 0 | 3 | 2 |  | 8 | 11 |  | 9 | 4 | 4 | 15 | 14 | 1 | 7 | 0 | 2 | 3 | 4 | 3 | 0 | 4
| AR02.2 | Epic implementation | AT001 | Number of errors | 15 |  | x | x | x |  |  | 3 |  | x | 1 |  | x |  |  | x |  |  |  | 2 |  |  |  | 0 | x | x |  |  |  | 2 |  |  | x |  | x |  |  |  | 2 | x |  |  |  |  | x | x |  |  | x | 4 |  |  | 0 | [14 empty] | 1 | bar: R045
| AR02.2 | Epic implementation | AT005 | Number of ready tasks | 18 | x | x |  | x |  | x | 4 | x | x | 2 |  | x | x | x |  |  | x | x | 5 |  | x |  | 1 | x |  |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 | x |  | 1 | [14 empty] | 4 | bar: R045; R051; R055 to R056
| AR02.2 | Epic implementation | AT007 | Number of subtasks of task | 5 |  |  | x |  |  |  | 1 |  |  | 0 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 4 | bar: R048 to R049; R054 to R055
| AR02.2 | Epic implementation | AT008 | Estimate | 22 |  | x |  | x |  | x | 3 |  | x | 1 |  | x | x | [5 empty] | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 |  |  | x | x | x | x | x |  |  |  | 5 | x |  | 1 | [14 empty] | 6 | bar: R046 to R049; R054 to R055
| AR02.2 | Epic implementation | AT010 | Design file | 14 | x | x | x | x |  |  | 4 |  |  | 0 |  |  |  | x |  |  |  |  | 1 |  |  |  | 0 |  |  | x |  |  | 1 | [8 empty] | 0 | [5 empty] | x | x |  | x | x | 4 |  |  | 0 | [14 empty] | 4 | bar: R045 to R048
| AR02.2 | Epic implementation | AT011 | Customer response time | 24 | x | x | x | x | x | x | 6 |  |  | 0 | x | x | x | x | x |  | x | x | 7 |  | x |  | 1 |  |  | x |  |  | 1 | [8 empty] | 0 | [5 empty] | x | x |  |  |  | 2 |  |  | 0 | [14 empty] | 7 | bar: R045; R048 to R049; R051; R053; R056; R058
| AR02.2 | Epic implementation | AT012 | Team response time | 17 | x | x |  | x |  |  | 3 |  | x | 1 | x |  |  |  |  | x | x | x | 4 |  | x |  | 1 |  |  | x |  |  | 1 |  |  |  | x |  | x | x |  | 3 | [10 empty] | 0 |  | x | 1 | [14 empty] | 3 | bar: R045; R050 to R051
| AR02.2 | Epic implementation | AT014 | Average of sub-tasks of task | 9 |  |  |  |  | x |  | 1 |  |  | 0 |  | x |  |  | x | x | x | x | 5 |  |  |  | 0 |  | x |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 2 | bar: R048 to R049
| AR02.2 | Epic implementation | AT015 | Standard deviation of sub-tasks | 9 |  |  |  |  | x |  | 1 |  |  | 0 |  | x |  |  | x | x | x | x | 5 |  |  |  | 0 |  | x |  |  |  | 1 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 2 | bar: R048 to R049
| AR02.2 | Epic implementation | AT016 | Average time spent on code review | 19 |  |  |  | x |  |  | 1 | x | x | 2 |  |  |  |  | x | x |  |  | 2 |  | x |  | 1 | [5 empty] | 0 | x | x | x |  | x | x | x |  | 6 |  |  |  | x | x |  |  |  | x |  | 3 | x | x | 2 | [14 empty] | 2 | bar: R048 to R049
| AR02.2 | Epic implementation | AT017 | Number of people doing code review | 12 | [6 empty] | 0 |  |  | 0 | x | [5 empty] | x |  | 2 |  |  |  | 0 | [5 empty] | 0 | x | x | x |  |  | x |  |  | 4 |  |  |  |  | x | [5 empty] | 1 | x | x | 2 | [14 empty] | 3 | bar: R045; R048 to R049
| AR02.2 | Epic implementation | AT018 | Number of comments after code review | 16 |  | x |  |  |  |  | 1 |  | x | 1 | x |  |  |  |  | x | x | x | 4 |  |  |  | 0 | [5 empty] | 0 | x | x | x | x | x |  | x |  | 6 | [10 empty] | 0 |  | x | 1 | [14 empty] | 3 | bar: R047 to R049
| AR02.2 | Epic implementation | AT019 | Average of unit tests for task | 8 | [6 empty] | 0 |  | x | 1 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | x | x | x |  | x |  |  |  | 4 |  |  |  | x | x | [5 empty] | 2 |  | x | 1 | [14 empty] | 0
| AR02.2 | Epic implementation | AT020 | Average of automated tests per task | 8 | [6 empty] | 0 |  | x | 1 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | x | x | x |  | x |  |  |  | 4 |  |  | x | x | [6 empty] | 2 |  | x | 1 | [14 empty] | 0
| AR02.2 | Epic implementation | AT021 | Average number of code returns to execution stage after review | 17 |  | x |  |  |  |  | 1 |  | x | 1 | x |  |  |  |  | x |  |  | 2 |  |  |  | 0 | x | x |  |  |  | 2 | x | x | x | x | x |  |  | x | 6 | [8 empty] | x |  | 1 | x | x | 2 | [14 empty] | 2 | bar: R048 to R049
| AR02.2 | Epic implementation | AT022 | Number of blocked tasks | 22 |  | x | x | x |  | x | 4 |  | x | 1 | x | x | x | x |  |  | x |  | 5 |  |  |  | 0 | x | x | x |  |  | 3 |  |  |  | x | x |  |  |  | 2 |  |  | x |  |  | x |  |  |  |  | 2 |  | x | 1 | [14 empty] | 4 | bar: R048 to R049; R051; R058
| AR02.2 | Epic implementation | AT026 | Percentage of time on meetings out of total work time | 14 |  |  |  | x |  | x | 2 |  | x | 1 | x |  | x | x |  |  | x | x | 5 |  | x |  | 1 | [5 empty] | 0 |  |  | x |  | x |  |  |  | 2 | [10 empty] | 0 | x | x | 2 | [14 empty] | 1 | bar: R045
| AR02.2 | Epic implementation | AT046 | Number of initial tasks | 9 | x | x |  |  | x | x | 4 |  | x | 1 |  | x |  |  |  |  | x | x | 3 |  |  |  | 0 |  |  |  |  | x | 1 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 0
| AR02.2 | Epic implementation | AT047 | Number of technical tasks | 11 |  |  |  | x |  |  | 1 | x | x | 2 |  |  |  |  | x | x |  |  | 2 |  |  |  | 0 | x | x | x |  |  | 3 |  |  |  | x |  |  |  |  | 1 | [6 empty] | x |  |  |  | 1 |  | x | 1 | [14 empty] | 0
| AR02.2 | Epic implementation | AT049 | Epic implementation time | 22 |  |  |  | x |  | x | 2 |  | x | 1 |  | x | x | x | x |  | x | x | 6 |  | x |  | 1 | x | x |  |  |  | 2 | x |  |  | x |  |  |  |  | 2 | [10 empty] | 0 | x | x | 2 | [14 empty] | 6 | bar: R045 to R046; R048 to R049; R051; R058
| AR02.2 | Epic implementation | AT050 | Number of in-development tasks | 23 |  | x |  |  |  | x | 2 | x | x | 2 |  | x | x | x |  |  |  |  | 3 |  | x |  | 1 | x | x | x |  |  | 3 | x |  | x |  | x |  |  |  | 3 |  | x | x | x | x |  | x |  |  |  | 5 |  |  | 0 | [14 empty] | 4 | bar: R048 to R049; R051; R056
| AR02.2 | Epic implementation | AT051 | Average of Estimate of Task | 22 |  | x |  | x |  | x | 3 |  | x | 1 |  | x | x | [5 empty] | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 |  |  | x | x | x | x | x |  |  |  | 5 | x |  | 1 | [14 empty] | 6 | bar: R046 to R049; R054 to R055
| AR02.2 | Epic implementation | AT052 | Number of Estimated Tasks | 14 |  | x |  |  |  |  | 1 | x | x | 2 | x |  |  | x |  |  |  |  | 2 |  |  |  | 0 | x |  | x |  |  | 2 |  |  | x | [5 empty] | 1 | [10 empty] | 0 |  |  | 0 | [14 empty] | 6 | bar: R045; R048 to R049; R051; R053; R058
| AR02.3 | Team | AR02.3 | Team | 89 | 0 | 0 | 0 | 6 | 0 | 1 |  | 3 | 2 | 0 | 3 | 1 | 1 | 1 | 0 | 1 | 3 | 2 | 0 | 2 | 2 | 3 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | 3 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 4 | 0 | 2 | 6 | 0 | 6 | 2 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 0
| AR02.3 | Team | AT013 | Average training time per person | 10 | [6 empty] | 0 | x |  | 1 | x | [5 empty] | x |  | 2 | x | x | x | 3 | [5 empty] | 0 | [8 empty] | 0 |  |  | x | [7 empty] | 1 |  | x | 1 | [14 empty] | 2 | bar: R045; R058
| AR02.3 | Team | AT026 | Percentage of time spent on meetings out of total team work time | 11 |  |  |  | x |  | x | 2 |  |  | 0 | x | [5 empty] | x | x | 3 |  | x |  | 1 | [5 empty] | 0 | [8 empty] | 0 | [8 empty] | x | x | 2 |  | x | 1 | [14 empty] | 2 | bar: R045; R058
| AR02.3 | Team | AT029 | Periodicity of documentation review | 11 |  |  |  | x |  |  | 1 |  |  | 0 | x | [6 empty] | x | 2 | x |  | x | 2 |  |  |  | x |  | 1 | [8 empty] | 0 | [8 empty] | x | x | 2 |  | x | 1 | [14 empty] | 2 | bar: R048 to R049
| AR02.3 | Team | AT053 | Team size | 23 |  |  |  | x |  |  | 1 |  | x | 1 | [5 empty] | x | x |  | 2 |  |  | x | 1 | x | x | x |  |  | 3 | x |  |  | x |  |  |  |  | 2 |  |  | x |  |  |  |  | x |  | x | 3 | x | x | 2 | [14 empty] | 8 | bar: R045 to R050; R052; R058
| AR02.3 | Team | AT003 | Velocity | 6 |  |  |  | x |  |  | 1 | x |  | 1 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 |  |  | x | [5 empty] | 1 | [10 empty] | 0 |  | x | 1 | [14 empty] | 2 | bar: R045; R051
| AR02.3 | Team | AT004 | Standard deviation of velocity | 5 |  |  |  | x |  |  | 1 | x |  | 1 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 |  |  | x | [5 empty] | 1 | [10 empty] | 0 |  |  | 0 | [14 empty] | 2 | bar: R045; R051
| AR02.3 | Team | AT054 | Team morale | 23 |  |  |  | x |  |  | 1 |  | x | 1 |  | x | x | x |  |  |  |  | 3 |  |  |  | 0 |  |  | x |  |  | 1 |  |  | x |  | x |  | x |  | 3 | x | [5 empty] | x | x |  | x | 4 | x | x | 2 | [14 empty] | 8 | bar: R045 to R047; R049 to R051; R053 to R054
|  |  | AR03 | Increment | 646 | 8 | 12 | 14 | 29 | 1 | 24 |  | 11 | 29 | 0 | 20 | 19 | 13 | 18 | 8 | 5 | 18 | 9 | 0 | 0 | 22 | 0 | 0 | 23 | 16 | 8 | 3 | 3 | 0 | 19 | 12 | 14 | 7 | 14 | 2 | 2 | 1 | 0 | 8 | 10 | 14 | 13 | 13 | 16 | 9 | 3 | 6 | 3 | 0 | 11 | 24 | 0 | 19 | 9 | 13 | 25 | 25 | 1 | 11 | 8 | 3 | 2 | 2 | 2 | 2 | 10 | 0
| AR03.1 | Product increment | AR03.1 | Product increment | 386 | 4 | 7 | 7 | 17 | 1 | 14 |  | 6 | 17 | 0 | 13 | 10 | 8 | 11 | 5 | 4 | 12 | 6 | 0 | 0 | 14 | 0 | 0 | 12 | 9 | 5 | 1 | 1 | 0 | 12 | 8 | 10 | 5 | 10 | 2 | 2 | 1 | 0 | 5 | 5 | 8 | 7 | 7 | 8 | 5 | 1 | 3 | 1 | 0 | 8 | 16 | 0 | 11 | 5 | 7 | 15 | 15 | 1 | 6 | 4 | 3 | 1 | 1 | 1 | 1 | 7 | 0
| AR03.1 | Product increment | AT006 | Number of implemented tasks | 30 | x |  | x | x |  | x | 4 | x | x | 2 | x | x | x | x |  |  | x |  | 5 |  | x |  | 1 | x |  |  |  |  | 1 | x | x | x |  | x |  |  |  | 4 | x | x | x | x | x | x |  |  |  |  | 6 |  | x | 1 | [14 empty] | 6 | bar: R045; R047 to R049; R051 to R052
| AR03.1 | Product increment | AT008 | Estimate | 23 |  | x |  | x |  | x | 3 |  | x | 1 |  | x | x | [5 empty] | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 |  |  | x | x | x | x | x |  |  |  | 5 | x |  | 1 | [14 empty] | 7 | bar: R046 to R049; R054 to R056
| AR03.1 | Product increment | AT016 | Average time spent on code review | 19 |  |  |  | x |  |  | 1 | x | x | 2 |  |  |  |  | x | x |  |  | 2 |  | x |  | 1 | [5 empty] | 0 | x | x | x |  | x | x | x |  | 6 |  |  |  | x | x |  |  |  | x |  | 3 | x | x | 2 | [14 empty] | 2 | bar: R048 to R049
| AR03.1 | Product increment | AT017 | Number of people doing code review | 11 | [6 empty] | 0 |  |  | 0 | x | [5 empty] | x |  | 2 |  |  |  | 0 | [5 empty] | 0 | x | x | x |  |  | x |  |  | 4 | [10 empty] | 0 | x | x | 2 | [14 empty] | 3 | bar: R045; R048 to R049
| AR03.1 | Product increment | AT018 | Number of comments after code review | 16 |  | x |  |  |  |  | 1 |  | x | 1 | x |  |  |  |  | x | x | x | 4 |  |  |  | 0 | [5 empty] | 0 | x | x | x | x | x |  | x |  | 6 | [10 empty] | 0 |  | x | 1 | [14 empty] | 3 | bar: R047 to R049
| AR03.1 | Product increment | AT021 | Average number of code returns to execution stage after review | 16 |  | x |  |  |  |  | 1 |  | x | 1 | x |  |  |  |  | x |  |  | 2 |  |  |  | 0 | x | x |  |  |  | 2 | x | x | x | x | x |  |  | x | 6 | [10 empty] | 0 | x | x | 2 | [14 empty] | 2 | bar: R048 to R049
| AR03.1 | Product increment | AT022 | Number of blocked tasks | 22 |  | x | x | x |  | x | 4 |  | x | 1 | x | x | x | x |  |  | x |  | 5 |  |  |  | 0 | x | x | x |  |  | 3 |  |  |  | x | x |  |  |  | 2 |  |  | x |  |  | x |  |  |  |  | 2 |  | x | 1 | [14 empty] | 4 | bar: R048 to R049; R051; R058
| AR03.1 | Product increment | AT023 | Sprint delay in days | 23 |  |  |  | x |  | x | 2 |  | x | 1 |  | x | x |  | x |  |  |  | 3 |  | x |  | 1 | x | x |  |  |  | 2 |  |  |  |  | x |  |  |  | 1 | x | x |  | x | x |  | x |  |  |  | 5 |  |  | 0 | [14 empty] | 8 | bar: R045 to R046; R048 to R049; R051; R053; R057 to R058
| AR03.1 | Product increment | AT024 | Time is allocated for demonstration meetings | 9 |  |  |  | x |  | x | 2 |  |  | 0 |  |  |  | x |  |  | x | x | 3 |  | x |  | 1 | [5 empty] | 0 | [8 empty] | 0 |  |  | x | [7 empty] | 1 |  | x | 1 | [14 empty] | 1 | bar: R045
| AR03.1 | Product increment | AT025 | Time is reserved for retrospective meetings | 7 |  |  |  | x |  |  | 1 |  |  | 0 |  |  |  | x |  |  | x | x | 3 |  | x |  | 1 | [5 empty] | 0 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 2 | bar: R045; R050
| AR03.1 | Product increment | AT026 | Percentage of time spent on meetings out of total team work time | 14 |  |  |  | x |  | x | 2 |  | x | 1 | x |  | x | x |  |  | x | x | 5 |  | x |  | 1 | [5 empty] | 0 |  |  | x |  | x |  |  |  | 2 | [10 empty] | 0 | x | x | 2 | [14 empty] | 1 | bar: R045
| AR03.1 | Product increment | AT028 | Number of hotfix | 29 | x | x | x | x | x | x | 6 |  | x | 1 | x |  |  | x | x |  |  |  | 3 |  | x |  | 1 | x | x | x |  |  | 3 | x |  | x |  | x |  |  |  | 3 | x |  | x |  |  | x | x |  | x |  | 5 | x | x | 2 | [14 empty] | 5 | bar: R048 to R049; R051; R053; R058
| AR03.1 | Product increment | AT029 | Periodicity of documentation review | 15 |  |  |  | x |  |  | 1 |  | x | 1 | x | [6 empty] | x | 2 |  |  |  | 0 |  |  | x | x | x | 3 | [8 empty] | 0 | [5 empty] | x | x | x | x | x | 5 |  | x | 1 | [14 empty] | 2 | bar: R048 to R049
| AR03.1 | Product increment | AT032 | Standard deviation of scope | 34 |  |  |  | x |  | x | 2 | x | x | 2 | x | x | x | x | x | x | x | x | 8 |  | x |  | 1 | x | x |  |  |  | 2 | x | x | x | x | x |  |  |  | 5 | x | x | x | x | x | [5 empty] | 5 |  | x | 1 | [14 empty] | 8 | bar: R045 to R049; R052 to R053; R058
| AR03.1 | Product increment | AT034 | Standard deviation of implemented tasks | 18 | x |  |  | x |  | x | 3 | x | x | 2 |  | x | x | x |  |  | x |  | 4 |  | x |  | 1 | x |  |  |  |  | 1 | [8 empty] | 0 |  | x | x | x | x | x |  |  |  |  | 5 |  | x | 1 | [14 empty] | 1 | bar: R052
| AR03.1 | Product increment | AT038 | Percentage of implemented tasks | 30 | x |  | x | x |  | x | 4 | x | x | 2 | x | x | x | x |  |  | x |  | 5 |  | x |  | 1 | x |  |  |  |  | 1 | x | x | x |  | x |  |  |  | 4 | x | x | x | x | x | x |  |  |  |  | 6 |  | x | 1 | [14 empty] | 6 | bar: R045; R047 to R049; R051 to R052
| AR03.1 | Product increment | AT040 | Percentage of tech tasks | 16 |  |  |  | x |  | x | 2 | x | x | 2 |  |  |  |  | x |  |  |  | 1 |  |  |  | 0 | x | x | x |  |  | 3 | x | x | [6 empty] | 2 | [5 empty] | x | x |  |  |  | 2 |  | x | 1 | [14 empty] | 3 | bar: R048 to R049; R051
| AR03.1 | Product increment | AT043 | Retrospective scope | 12 |  |  | x | x |  | x | 3 |  | x | 1 | x | x | [6 empty] | 2 |  | x |  | 1 | [5 empty] | 0 | x |  | x | x |  |  |  |  | 3 | [10 empty] | 0 |  |  | 0 | [14 empty] | 2 | bar: R045; R058
| AR03.1 | Product increment | AT044 | Percentage difference between scope and retrospective scope | 21 |  | x | x | x |  | x | 4 |  | x | 1 | x | x |  | x |  |  | x |  | 4 |  | x |  | 1 | x | x |  |  |  | 2 | x | [7 empty] | 1 | [10 empty] | 0 | x | x | 2 | [14 empty] | 6 | bar: R045 to R049; R058
| AR03.1 | Product increment | AT045 | Standard deviation of the retrospective scope | 21 |  | x | x | x |  | x | 4 |  | x | 1 | x | x |  | x |  |  | x |  | 4 |  | x |  | 1 | x | x |  |  |  | 2 | x | [7 empty] | 1 | [10 empty] | 0 | x | x | 2 | [14 empty] | 6 | bar: R045 to R049; R058
| AR03.2 | Product release plan | AR03.2 | Product release plan | 260 | 4 | 5 | 7 | 12 | 0 | 10 |  | 5 | 12 | 0 | 7 | 9 | 5 | 7 | 3 | 1 | 6 | 3 | 0 | 0 | 8 | 0 | 0 | 11 | 7 | 3 | 2 | 2 | 0 | 7 | 4 | 4 | 2 | 4 | 0 | 0 | 0 | 0 | 3 | 5 | 6 | 6 | 6 | 8 | 4 | 2 | 3 | 2 | 0 | 3 | 8 | 0 | 8 | 4 | 6 | 10 | 10 | 0 | 5 | 4 | 0 | 1 | 1 | 1 | 1 | 3 | 0
| AR03.2 | Product release plan | AT001 | Number of errors | 17 |  | x | x | x |  |  | 3 |  | x | 1 |  | x |  |  | x |  |  |  | 2 |  |  |  | 0 | x | x |  |  |  | 2 |  |  | x |  | x |  |  |  | 2 | x | x | x | x | x | x |  |  |  |  | 6 |  |  | 0 | [14 empty] | 1 | bar: R045
| AR03.2 | Product release plan | AT006 | Number of implemented tasks | 30 | x |  | x | x |  | x | 4 | x | x | 2 | x | x | x | x |  |  | x |  | 5 |  | x |  | 1 | x |  |  |  |  | 1 | x | x | x |  | x |  |  |  | 4 | x | x | x | x | x | x |  |  |  |  | 6 |  | x | 1 | [14 empty] | 6 | bar: R045; R047 to R049; R051 to R052
| AR03.2 | Product release plan | AT008 | Estimate | 22 |  | x |  | x |  | x | 3 |  | x | 1 |  | x | x | [5 empty] | 2 |  | x |  | 1 | x | x | x |  |  | 3 | [8 empty] | 0 |  |  | x | x | x | x | x |  |  |  | 5 | x |  | 1 | [14 empty] | 6 | bar: R046 to R049; R054 to R055
| AR03.2 | Product release plan | AT029 | Periodicity of documentation review | 15 |  |  |  | x |  |  | 1 |  | x | 1 | x | [6 empty] | x | 2 |  |  |  | 0 |  |  | x | x | x | 3 | [8 empty] | 0 | [5 empty] | x | x | x | x | x | 5 |  | x | 1 | [14 empty] | 2 | bar: R048 to R049
| AR03.2 | Product release plan | AT031 | Number of open versions | 18 |  |  |  | x |  | x | 2 | x | x | 2 |  | x |  | x |  |  |  | x | 3 |  | x |  | 1 | x | x |  | x | x | 4 | x |  |  | x |  |  |  |  | 2 | [7 empty] | x | x | x | 3 |  |  | 0 | [14 empty] | 1 | bar: R045
| AR03.2 | Product release plan | AT035 | Number of completed sprints | 23 | x |  | x | x |  | x | 4 | x | x | 2 |  | x | x | x |  |  | x |  | 4 |  | x |  | 1 | x |  |  |  |  | 1 | [8 empty] | 0 |  | x | x | x | x | x |  |  |  |  | 5 |  | x | 1 | [14 empty] | 5 | bar: R045; R048 to R049; R051 to R052
| AR03.2 | Product release plan | AT038 | Percentage of implemented tasks | 30 | x |  | x | x |  | x | 4 | x | x | 2 | x | x | x | x |  |  | x |  | 5 |  | x |  | 1 | x |  |  |  |  | 1 | x | x | x |  | x |  |  |  | 4 | x | x | x | x | x | x |  |  |  |  | 6 |  | x | 1 | [14 empty] | 6 | bar: R045; R047 to R049; R051 to R052
| AR03.2 | Product release plan | AT039 | Standard deviation of number of tasks | 36 | x | x |  | x |  | x | 4 |  | x | 1 | x | x | x | x | x | x | x | x | 8 |  | x |  | 1 | x |  |  |  |  | 1 | x | x | x | x | x |  |  |  | 5 |  | x | x | x | x | x | x |  | x |  | 7 |  | x | 1 | [14 empty] | 8 | bar: R045; R048 to R049; R051 to R052; R056 to R058
| AR03.2 | Product release plan | AT040 | Percentage of tech tasks | 16 |  |  |  | x |  | x | 2 | x | x | 2 |  |  |  |  | x |  |  |  | 1 |  |  |  | 0 | x | x | x |  |  | 3 | x | x | [6 empty] | 2 | [5 empty] | x | x |  |  |  | 2 |  | x | 1 | [14 empty] | 3 | bar: R048 to R049; R051
| AR03.2 | Product release plan | AT043 | Retrospective estimate | 11 |  |  | x | x |  | x | 3 |  | x | 1 | x | [7 empty] | 1 |  |  |  | 0 | x | x |  |  |  | 2 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0 | [14 empty] | 4 | bar: R046 to R049
| AR03.2 | Product release plan | AT044 | Percentage difference between scope and retrospective scope | 21 |  | x | x | x |  | x | 4 |  | x | 1 | x | x |  | x |  |  | x |  | 4 |  | x |  | 1 | x | x |  |  |  | 2 | x | [7 empty] | 1 | [10 empty] | 0 | x | x | 2 | [14 empty] | 6 | bar: R045 to R049; R058
| AR03.2 | Product release plan | AT045 | Standard deviation of the retrospective estimate | 21 |  | x | x | x |  | x | 4 |  | x | 1 | x | x |  | x |  |  | x |  | 4 |  | x |  | 1 | x | x |  |  |  | 2 | x | [7 empty] | 1 | [10 empty] | 0 | x | x | 2 | [14 empty] | 6 | bar: R045 to R049; R058
[43 empty] | 0 | [10 empty] | 0 |  |  | 0
[15 empty] | 0 | [8 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | [8 empty] | 0 | [10 empty] | 0 |  |  | 0

## Artifacts
ID | Artifact | Description
AR01 | Product
AR01.1 | Product Backlog | A newly compiled, organized list of what is needed to improve the product
AR01.2 | Product Goal | The product goal describes the future state of the product, which can be the planning goal of the Scrum team
AR01.3 | Epic Discovery | The process of holding sessions with stakeholders to elicit high-level customer needs for the implementation of a specific functionality module
AR01.4 | Design Discovery | The process of gathering detailed product design requirements and creating a list of user stories
AR01.5 | Technical Debt Backlog | A list of tasks to maintain product architecture and code hygiene
AR01.6 | Product Roadmap | A strategic plan that defines a goal or desired outcome and identifies the key steps or milestones needed to achieve it
AR02 | Sprint
AR02.1 | Sprint Backlog | A sprint to-do list consists of a sprint goal, a set of product backlog items selected for the sprint, and an actionable plan to achieve product increments
AR02.2 | Epic Implementation | The process that a Scrum project team performs during a sprint or multiple sprints to ensure that all user stories in a feature module meet the definition of work done
AR02.3 | Team | A team is a self-organizing, cross-functional group of individuals who collaboratively work together to deliver valuable increments of a product within a sprint
AR03 | Increment
AR03.1 | Product Increment | The set of tasks that meet the definition of completed work during a sprint
AR03.2 | Product Release Plan | A collection of information to help define the release scope, milestones and timelines.

## Risks
ID | Risk
RC1 | Requirements
R001 | Undefined requirements
R002 | Unclear requirements
R003 | Incorrectly defined requirements
R004 | Unmet requirements and scope creep
R005 | Resource misallocation due to many competing priorities
R006 | Poor prioritization and unclear vision
RC2 | Project Management
R007 | Lack of sufficient tasks for the team that match their competences
R008 | Lack of accountability in addressing missed deadlines and delayed sprints
RC3 | Communication
R009 | Lack of communication among team members
R010 | Low client engagement and misalignment of requirements
R011 | Delays due to slow client responses
R012 | Unclear project vision and progress
R013 | Rework of completed tasks
R014 | Rework due to lack of communication
R015 | Poor communication
R016 | Lack of structured information
RC4 | Technology
R017 | Excessive time on training
R018 | Inadequate understanding of Scrum processes
R019 | Inefficient onboarding process
RC5 | Design
R020 | Delays due to task interdependencies
R021 | Scope increase due to tasks dependencies
R022 | System-wide impact overlooked during task execution
R023 | Use of outdated software versions
R024 | Untraceable tasks
RC6 | Coding
R025 | Difficult to maintain the code without code standards
R026 | Difficult to understand and support code
R027 | Reduced performance
R028 | Increasing technical debt
R029 | Poor code quality
R030 | Lack of code improvement support
R031 | Lack of code review feedback
R032 | Redundant development of existing functionality
RC7 | Testing
R033 | Lack of attention to detail by testers
R034 | Testing lagging behind development in the sprint
R035 | Poor QA-developer collaboration leading to uncommunicated changes across the system
R036 | Insufficient unit testing by developers
R037 | Challenges in unit testing legacy code
R038 | Lack of test scenarios for QA specialists
R039 | Unassessed impact of changes on other system areas
R040 | Overwriting documentation among team members
R041 | Outdated documentation
R042 | Dependency on key team members due to poor documentation
RC8 | Human
R043 | Overlooking team expertise due to inadequate task allocation
R044 | Shortage of necessary specialists in team
RC9 | Agile Ceremonies
R045 | Inefficient Scrum integration
R046 | Overestimated tasks
R047 | Underestimated tasks
R048 | Inaccurate task evaluation without full requirement insight
R049 | Tasks evaluated without technical constraints in mind
R050 | Ineffective retrospective meetings
R051 | Decreasing scope completion in sprint
R052 | Increased sprint output with decreased quality
R053 | Mismatch in planned and actual sprint task completion
R054 | Inefficient task splitting
R055 | Excessive number of small tasks
R056 | Insufficient sprint backlog
R057 | Overloaded sprint backlog
R058 | Inaccurate sprint velocity forecasting